EDdy Dynamics, mIxing, Export, and Species composition

(EDDIES)

Project Summary and Cruise Logistics

Updated August 25, 2003

Contents:

1. Hypotheses

2. Scenarios

3. Objectives

4. Selection of the target eddy feature

5. Sampling operations

6. Measurements

7. Berthing

8. Related projects and proposals

9. Project timeline

Appendices

A. Detailed sampling information: Café Thorium

B. Detailed sampling information: Siegel

C. Detailed sampling information: Hansell

D. Tracer cruise logistics: Ledwell

1. Hypotheses

Prior results have documented eddy-driven transport of nutrients into the euphotic zone and the associated accumulation of chlorophyll. However, several key aspects of mesoscale upwelling events remain unresolved by the extant database, including: (1) phytoplankton physiological response, (2) changes in community structure, (3) impact on export out of the euphotic zone, (4) rates of mixing between the surface mixed layer and the base of the euphotic zone, and (5) implications for biogeochemistry and differential cycling of carbon and associated bioactive elements. This leads to the following hypotheses concerning the complex, non-linear biological regulation of elemental cycling in the ocean:

H1: Eddy-induced upwelling, in combination with diapycnal mixing in the upper ocean, introduces new nutrients into the euphotic zone.

H2: The increase in inorganic nutrients stimulates a physiological response within the phytoplankton community.

H3: Differing physiological responses of the various species bring about a shift in community structure.

H4: Changes in community structure lead to increases in export from, and changes in biogeochemical cycling within, the upper ocean.

2. Scenarios

There are several scenarios in which this chain of hypotheses could be linked or broken.  These include, but are not necessarily limited to, the following:

S1: Nutrient input to the euphotic zone simply increases the rate of production by the background species assemblage dominated by picoplankton; impacts on biogeochemical cycling are nil.

S2: Increased nitrate availability stimulates a bloom of diatoms; silica-rich organic material produced in the bloom sinks rapidly out of the euphotic zone once the nutrients are exhausted.

S3: Shoaling isopycnals transport DIP closer to the surface, facilitating nitrogen fixation by Trichodesmium or perhaps vertically migrating diatoms with symbiotic bacteria; nitrogen-rich organic material produced during the bloom is exported primarily in dissolved form.

S4: The eddy feature accommodates a change in community structure and biomass of consumers that produce rapidly sinking particles.

3. Objectives

The following objectives are designed to test hypotheses H1-H4 and distinguish between the scenarios S1-S4 in which the chain of hypotheses are linked or broken.

O1:  Measure the enhancement of inorganic nutrient availability brought about by eddy-induced upwelling.

O2:  Measure the phytoplankton physiological response to increased nutrients.

O3:  Assess shifts in species composition associated with the eddy disturbance.

O4:  Quantify the impact of the eddy disturbance on upper ocean biogeochemical cycling: measure elemental inventories, primary production, and export.

O5:  Assess the interaction between eddy-driven isopycnal transport processes and diapycnal fluxes in and below the mixed layer (quantifies the reversibility of the eddy-induced transport; specifically, how is the oxygen anomaly “left behind” and eddy-driven new production event).

4. Selection of the target eddy feature

Real-time analysis of altimetric observations will provide maps of the eddy field prior to and during our sampling operations.

As far as we know, there are three different types of mid-ocean eddies in the Sargasso Sea: cyclones, anticyclones, and mode-water eddies (MWEs).  Cyclones and MWEs are of interest to this project, as both tend to displace upper ocean isopycnals toward the surface, causing nutrient input into the euphotic zone.  Whereas cyclones are identifiable in satellite altimetry by virtue of their negative sea level anomaly (SLA), MWEs are not distinguishable from anticyclones on the basis of altimetry alone because both result in positive SLA.  In principle, satellite-based SST could distinguish these two, as anticyclone and MWEs would be characterized by warm and cold SST anomalies, respectively.  However, given the paucity of reliable SST imagery in the Sargasso Sea during summer, we will likely have to rely on in situ measurements to unequivocally distinguish MWEs from anticyclones.

Eddy age is another key issue.  Whereas an intensifying cyclone will have upwelling in its center, the isopycnals in the interior of a decaying cyclone will be downwelling.  The earlier phase of the eddy’s lifetime will be when nutrient injection and the associated biological response occur.

Summary of desirable characteristics for the target eddy:

1. Young

2. Strong

3. Intensifying

4. Chemical impact discernible in real time (optical NO3 sensor)

5. Biological impact discernible in real time (fluorometry, microscope counts, VPR?)

6. Cyclone versus MWE?

a. unequivocal satellite determination favors cyclones

b. trapping of near-inertial motions and possible enhanced mixing favors MWEs

c. some of the big events at BATS have been MWEs

Jenkins (1988) Summer 1986 event

McNeil et al. (1999) July 1995 eddy

7. Proximity to BBSR: must be within 1 day’s steam for Weatherbird II

Clearly, it will behoove us to sample several eddies during the first survey cruise prior to making a decision about which eddy we wish to spend the rest of the summer in.

5. Sampling operations

Once the target feature is chosen, intensive sampling will begin:

Oceanus: 2 snapshots per “Survey Cruise”

Weatherbird II: 2 sections per “Section Cruise”

Timeline:

6/10 – 7/2	7/5 – 7/20	7/23 – 8/9	8/12 – 8/27

Oceanus  		Survey 1 	Tracer 1 	Survey 2 	Tracer 2

Weatherbird II 	Sections 1			Sections 2

Note that five days of ship time (originally requested for a test cruise in April) have been added to the first survey cruise.  This shifts the timing of all subsequent cruises from an earlier version of the schedule.

6. Measurements

Remote sensing

Altimetry, ocean color, SST		McG/Siegel

Oceanus Surveys

XBT 					McG

ADCP 					McG

CTD + FRRF + Optical NO3 		McG/Falko/Siegel

Niskin water sampling

HPLC

NO3, PO4, SiO2

POC, PON

Helium/Tritium		Jenkins

Microscope counts		Falko

Bio-optics (casts)			Siegel

Bio-optical drifter			Siegel

VPR?					Davis

Weatherbird II Sections

NO3, PO4, SiO2; HPLC; POC, PON	Bates		16-20 depths; 24-place rosette

14C Productivity			Bates

Sediment traps (150m)		Bates

TCO2, pCO2, O2			Bates

DOC, DON, DOP, δ15N(PON)	Hansell

Thorium-based export			Buesseler	2hr casts edge/middle/center

FRRF					Falko

Oceanus Tracer Cruises

SF6					Ledwell	ship available half time

Gliders

CTD, fluor., opt. backscatter, PAR	Fratantoni

Notes:

Will there be a sediment trap outside the eddy? Can BATS serve as the control?

FRRF work at night; can dark adapt (1 hour delay)

Falkowski may bring along a FlowCAM

Niskin sampling depths:

Prior work used 0,20,40,60,80,100,120,140,200,300,500,700 (12 depths)

Should we increase resolution near the base of the euphotic zone?

Bottle sample inventory

Oceanus: 2 cruises x 2 snapshots x 25 stations x 12 depths = 1200 samples

Weatherbird II: 2 cruises x 2 sections x 7 stations x 12 depths = 336 samples

Total: 1536 samples

Utilizing down time on Ledwell cruises

Sampling sled stays attached to hydro wire

Sample 4-5 hours; process 4-5 hours [ship available during processing]

Oceanus salt bottles to be stored aboard ship and run upon return to WHOI; experience suggest storage period of up to one year is acceptable, provided that bottle neck and cap are dried thoroughly prior to closure.

Logistics:

Ship gear to Bermuda or pack on Oceanus?

7. Berthing

Oceanus Survey Cruises [capacity 14-18]

McGillicuddy		6

Falkowski		2

Siegel			1

Jenkins		2

Fratantoni		2-3

[Davis]			2

[Brzezinski]		2

[Armbrust]		1-2

Oceanus Tracer Cruises [capacity 14-18]

Ledwell		6

Weatherbird II  [capacity 10]

Bates			3*

Hansell		1*

Buesseler		2

Falkowski		2

[Carlson]		1-2

[Steinberg]		1-2

*These 4 people comprise the hydro team that will run 12 on / 12 off shifts.

8. Related Projects and Proposals

Fratantoni		Gliders

Davis			VPR

Oakey/Ledwell	Finestructure

Steinberg		Zooplankton net tows

Carlson		prokaryotic community structure and DOM dynamics

Armbrust		genetic diversity in eukaryotes

Shipe/Brzezinski	N and Si uptake

Benitez-Nelson et al.	Hawaiian Eddy Project

9. Project timeline

2003

July 1		Start Date

July 23		First PI meeting, Woods Hole

2004

February	Second PI meeting, ASLO/TOS Conference, Honolulu

Summer	Field Work

2005

Winter		PI meeting: analysis of ’04 and planning for ‘05

Summer 	Field Work

2006

Winter		PI meeting: synthesis and manuscript preparation

June 30	End date

Appendix A: Detailed sampling information - Café Thorium

# 4 Liter sampling plan

- Approximate number of 4 liter samples: 120-140/cruise

This plan is based on 10-12 point profiles collected at each station.

- 7 stations to be sampled during BGC section 1 will include: 2 out stations, 2 edge stations, 2 middle stations, 1 center station.   6 stations sampled on BGC section 2 include: 1 out station (excluding the most recent out station), 2 edge stations, 2 middle stations, 1 center station.

- 1 deep water (4000 meter) calibration cast is required.  10 samples for 234Th calibration collected.

- We estimate a 4l sample collection rate of  20/day.

- Approximately 3 days are needed for sample processing.  Will require 2 days at the dock to finish processing.

- All beta counting will be performed back at WHOI.

- In ships lab, rack space for filtration apparatus will require 4x8 feet of wall space.  (We are requesting the aft section of the WB II main science lab.  See deck layout)

- Berthing requirements: 2 persons on each leg.  (Need to find 1 person for June ’04 and July “04 cruise)

- Jan ’05:  recovery chemistry at WHOI (Need 1 person for lab work: Claudia student?, Pinghe Cai?)

# Pump sampling plan

- A total of 8 stations sampled BCG Sections 1 and 2.  Section 1: 2 out stations, 2 edge stations, 1 eddy center.  Section 2: 1 eddy center, 1 edge, 1 out

This plan is based on 4 point profiles collected at each station.

Section 1

Section 2

- Casts will consist of 4 pumps deployed simultaneously for 2 hours, or 2 casts with 2 pumps deployed for a total of 4 hours.  Total volume of 500l at 8 l/min.  1 hour total deployment/recovery time.

- Wire time required:  16 hours w/4 pumps, 32 hours w/2 pumps.

A request has been made to have 4 pumps available so as to minimize wire time requirements.

- Pump deployment will require separate hydro-wire and winch.

- Each pump will be fitted with a 142 mm 54um screen followed by a 1.0 um quartz filter.  Total of 64 particulate samples for C/Th analysis and counting.  (32 silver filters/cruise)

Other:

- Will there be a drogued PITS traps deployed by BATS team?

Should a trap be shipped back from Hawaii for the July ’04 cruise?

- Counting: 54 um samples need to be counted first. (Typical BATS activity for these samples is as low as 0.6 cpm)  3 days counting time required for all silver filters.

- 14 days required for counting 4l samples.  All counting finished in 14-16 days from collection date.  (BATS samples are around 3 cpm after 10 days)

Appendix B: Detailed sampling information – Siegel

The UCSB group will make three field measurements in support of EDDIES 2004.

1. Spar array between the two survey cruises

2. Profiling spectroradiometery casts to characterize UW light field in and around the eddy from the survey cruises

3. Autonomous NO3 sensor on the survey CTD package

The spar array will be made up of 7 SBE-39s (temperature loggers with 2 millidegree accuracy) and 3 WETLabs chl-fl/backscatter sensors (ECO-FL-NTUSB; http://www.wetlabs.com/Products/eco/flntu.htm).  There may be more instrumentation deployed depending on budgets, etc.  The spar will have a surface light and an ARGOS transmitter (maybe two) and will be drouged with a holey sock at the depth of the tracer release.  Dave Menzies can handle this and will be on both cruises; modulo some help on deck deploying and retrieving.

The profiling spectroradiometer is a Satlantic SPMR system with 12 or so channels of downwelling irradiance, upwelling radiance, chl-fl and temperature on the fish and a surface sensor for measuring incident downwelling irradiance.  The SPMR is a hand-lowered instrument that is designed to minimize ship shadows. There will be a small hand reel for the cable that needs to be bolted to the deck.  We want casts from daylight hours (preferably 0900 to 1600) and normally deploy from the stern with stern facing the sun.  The deployment takes two people minimally; one running the aquisition computer and one handling the kevlar cable.  With Dave M going alone from UCSB, we will need some help with this (either on deck or in the lab).  The deployments take less than 20 minutes per station.  The surface sensor needs have an unobstructed view of the sun, be able to run cables into the lab computer and have a seawater supply via a garden hose (for cooling).  We've done this on the Ron Brown before and will on the Knorr this fall.  The computer should be near access to the fantail and we may want to use radios to communicate from lab to deck.

The last is that we'll be responsible for the care and feeding of the optics sensors on the survey CTD and the UCSB NO3 optical nitrate sensor.  This should be easy but will require us to do air cals of the transmissometers, etc.

I figure we will need 3 to 4 feet of lab space for all of this although a good deal of storage for the spar equipment.  I'm not sure of hazmats at this time, but I think we'll have ethanol for cleaning optical windows.

Appendix C: Detailed sampling information – Hansell

Water budget:

DOC 100 ml

DON 100 ml

DOP 200 ml

Del 15N PON  (4 L, but only at the shallowest depths).  Perhaps we could take some of this with bucket casts, or perhaps these samples should come from the survey.

Appendix D: Tracer cruise logistics – Ledwell

Injection/Initial Sampling Cruise

R/V Oceanus, Ledwell, Chief Scientist

5 July 2004 – 20 July 2004, Bermuda to Bermuda

15 days actually at sea

Day	Activity

- Steam to site

- Arrive at site, start XBT survey

- Continue survey, test injection gear, Continue survey

- Inject tracer, Deploy floats, Deploy Seahorse

- Let the ship air out, while shifting to sampling mode

- Sampler Tow 1

- Sampler Tow 2

- Sampler Tow 3, Check out Seahorse, redeploy

- Sampler Tow 4

- Sampler Tow 5

- Sampler Tow 6

- Sampler Tow 7

- Sampler Tow 8, Turn Seahorse around

- Steam to port

- Steam to port

Seahorse is a free-drifting, profiling finestructure instrument from BIO, whose use is not yet funded, but just proposed to NSF P.O. program.  If it is funded, it is hard to say how much ship time it will take.  It is possible that it will take very little.  Each deployment and recovery might take just a few hours.

Days 3 and 4 will be devoted to testing the injector and getting the tracer in. Switching from the injection sled to the CTD/Rosette frame would be impractical during this period.  On the other hand we could be finished earlier than planned if all goes well.  Injection will be done from the waist of the Oceanus using the starboard CTD boom.  On Day 5 we’ll change over to the sampling system – this means shifting the CTD cable to the A-frame on the stern.  I believe that we could arrange the termination so that it is easy to switch from the sampler sled to a conventional CTD/Rosette frame.  It would be best to do the CTDs from the stern, rather than to move the wire back and forth between the A-Frame and starboard CTD boom, but even this might be arranged with the proper blocks.

Sampling tows

We hang 10 to 12 integrating samplers below the sampling sled, then the sled at the end of the CTD cable, then 10 to 12 more integrating samplers.  On the sampling sled is a CTD, a 50-chamber sampling system, with the samplers filling sequentially, and a rosette pylon with a few 1.2 L Niskin bottles.  It takes about 90 minutes to deploy (longer the first time).  We then get the sled on the target surface, trip the bottles, and tow for 10 hours.  Recovery of the system takes another 90 minutes or so.  We should allow 14 hours or wire time for the whole operation.  We do one of these each day, leaving 10 hours of ship and wire time free for other things.  Ordinarily we arrange it so the tow is during the night, e.g. from 2200 to 0800, so the wire is busy from 2000 to 1000.  There is nothing sacred about this night time schedule for us.  We could tow during the days instead, if someone wanted the wire at night.  But it would be hard on us to switch back and forth a lot from days to nights for the tows.

Sampling Cruise

R/V Oceanus, Ledwell, Chief Scientist

12 August to 27 August 2004

Bermuda to Woods Hole (as scheduled presently)

15 days actually at sea.

Once we are at the site and decide where we want to sample, these days are all the same, again with 14-hours of wire time each day to do the sampling tows.  All would be the same as described above.

The SeaHorse would be part of the program and would require recovery and redeployment at the start of work and final recovery at the end of work.

The tracer group would use 6 berths, at least, and as presently planned.  Extra hands gratefully accepted.  The SeaHorse would add 2 people, if funded. But Oceanus has 13 berths and 17 if the berthing van is added.

We need about 60% of the space in the main lab for tracer analysis, CTD and ADCP operations, and data analysis stations.  The wet lab will be used for injection gear during the first cruise.  We will bring a 20-foot van for the sampling gear for both cruises.